## Sheet1
Week | Dates | Phase | Owner | Key Tasks | Deliverables | Status | Notes
1 | 2025-09-29 | Project Setup & Scoping | Team | Define the project objectives and scope, identify and document data sources, outline KPIs and success metrics, and set up data storage and version control. | Project charter and defined objectives document | Complete
2 | 2025-10-06 | Data Acquisition | Jay | Collect raw data from all identified sources, verify data access and permissions, assess data quality, and document data fields and formats. | Compiled raw dataset with data source documentation | Complete | Still compilng player statistic and roster data
3 | 2025-10-13 | Data Cleaning I | Jay | Handle missing values, standardize data types and formats, and identify and remove duplicates or outliers. | Initial cleaned dataset (version 1) | Complete
4 | 2025-10-20 | Data Cleaning II & Integration | Jay | Merge data from multiple sources, validate consistency across key fields, and finalize the data dictionary. | Fully cleaned and integrated master dataset with data dictionary | In Progress
5 | 2025-10-27 | Data Compilation & Exploration | Team | Conduct exploratory data analysis (EDA), generate summary statistics and visualizations, and identify correlations, patterns, and anomalies. | Exploratory data analysis summary and visual insights | In Progress
6 | 2025-11-03 | Pre-Modeling Preparation | Tea | Engineer relevant features, split the dataset into training and test sets, and normalize or encode variables as needed for modeling. | Model-ready dataset with engineered features | Not Started
7 | 2025-11-10 | Model Development | Tea | Develop baseline models using selected algorithms, evaluate model performance metrics, and refine parameters for improved accuracy. | Baseline model results and performance summary | Not Started
8 | 2025-11-17 | Model Validation & Refinement | Tea | Perform cross-validation and error analysis, compare alternative models, and document final model performance and rationale. | Validated final model with documentation of evaluation metrics | Not Started
9 | 2025-11-24 | Reporting & Visualization Build | Shriniketh | Create dashboards and visualizations, summarize key insights, and draft the written report or presentation materials. | Draft report and visualization dashboard | Not Started
10 | 2025-12-01 | Final Review & Presentation | Team | Review and quality-check all outputs, finalize and deliver the presentation to stakeholders, and archive project files and documentation. | Final report, presentation deck, and archived project files | Not Started
Formulas:
Dates = [Dates, row below]-7